## Slide 1: Making and implementing policy
Rohan Samarajiva & Helani Galpaya
Yangon, 26 July 2014
This work was carried out with the aid of a grant from the International Development Research Centre, Ottawa, Canada.

## Slide 2: Objective
Highlight challenges of building effective organizations to achieve objectives set out in LAW and implement POLICY
  In case of a law that requires action by private parties (e.g., offering of mobile telecom services), regulation
  Where direct government action is required

## Slide 3: E Sri Lanka program architecture
E leadership
Infrastructure
E society
E government
E business

## Slide 4: Diagnosing road blocks
Existing organization, CINTEC, was unable to perform apex function
  New agency?
  What to do with old one?
Coordinating with multiple government agencies to advance e government was seen as the greatest challenge
  Authority higher than individual Ministers?

## Slide 5: Solution
Company limited by guarantee, fully owned by the government
Private-sector culture from inception
  Advertisements issued during holidays when expatriates were back in Sri Lanka
  Interviews for leadership positions conducted over video links
  Private sector salaries and benefits
  COO of leading IT company recruited to lead ICT Agency

## Slide 6: Policy  Implementation
‘Seed’ grant
  to get the ICT Agency (ICTA) started
  Buildings, people, resources
Project Preparation stage
  Prepare necessary documents
    WB + ICTA staff work on final project details (project appraisal document) that is approved by the WB
  Pilot projects: for some quick wins
    eHRM (electronic Human Resource Management)
    Agricultural Price Information system
    A few community access tele-centers

## Slide 7: From 4 programs  more
ICT Leadership & Institutional Development
Re-Engineering Government Services
ICT Capacity Building
ICT Investment and Private Sector Development
Technical Architecture, standards, specifications
eSociety
Information Infrastructure

## Slide 8
Finally, signing large grant (USD 53 million grant) agreement
  Under a new government
  About a year after ICT Agency was Formed

## Slide 9: E-Society
Aim: to develop ICT applications that help the most disadvantaged
Primary Mechanism: e-Society Dev. Fun
  source the best ideas from developers, NGOs through competitions
  give funding, mentoring
Move Business Process Outsourcing to rural areas
  Companies in Colombo outsourcing to rural
Some success stories
  E.g. audio program to aid reading by visual disabled persons

## Slide 10: Infrastructure
Networks:
  A govt network: to link central & regional offices (Done)
  Extension of the fiber-optic network and connectivity to rural areas (not done)
Access points via Telecenters
  Telecenters: 500+ planned, primarily for rural areas
  Private sector operated; initial capital from govt.
  Initially selected competitively…later changed
  A success?

## Slide 11: ICT Human Resource Development
Training government employees
  Mass trainings
Training private sector
  Linked to the ICT Capacity Building Fund
Training citizens
  Select certified training organizations
  They run ‘ICT Driving License’ basic certification program
  Weekly TV program
Indicated success: increased ICT literacy rates

## Slide 12: E-Business: to develop the ICT private sector in Sri Lanka
Aim 1: Increase investment in the sector. Brand Sri Lanka as outsourcing destination – increase firms exporting more services (software, BPO..)
Aim 2: Use e-Government procurement as a way to develop local ICT private sector companies
Activities:
  Bring industry together formally: umbrella association
  Create a vision: strategic planning process
  Brand the country as an outsourcing destination
  Take firms to trade shows  increase visibility
  Increase skills of Sri Lankan firms: ICT Private Sector Capacity Building Fund
  Create awareness of BPO sector among people
Today a success story

## Slide 13: E-Government
Model:
  Re-engineer government services
  Get private sector (software) companies to implement the software to automate
Prioritized list of e-Gov services
  Ranked by impact, usage and feasibility
  Entrenched interests  inability to implement projects at the top of the list
  End up doing what you can
Perceptions of the ICT Agency
  As outsiders. Not software experts. Not government either
ICT Capacity in Government : non-existent
Chief Information Officer appointed at each govt. office
  A long process
  Use this person as champion of process

## Slide 14: Much talk, no early results
Mismatch of interests, resources
  Money (at ICT Agency)
  Technical Knowledge (ICT Agency)
  Ownership of the service (Government Dept/Ministry)
  Disruptions to work during implementation (Dept./Ministry)
  High likelihood of failure
Long time needed from concept to finish
  Study processes; re-engineer them
  Identify system requirements
  Procurement process (int’l)
  Implement the system
E.g. ePensions project
Result: 2.5 years after inception, no e-Gov project implemented
But HUGE expectations
  Media, others: setting expectations

## Slide 15: Working ‘outside’ the government system: 1919 Government Information System
Background: need for quick win e-Gov project
  Long time before e-Gov services become reality.
  To counter negative perceptions
Lack of information HOW TO ACCESS GOVT. SERVICES
  Multiple trips to government office, wasted time, costs
  Low internet use  websites not a full solution
Solution: a call center
  Polite, helpful, fast
  Service-based, not department based
Choices
  Train govt. workers to run a call center
  Something faster?

## Slide 16
Tapping the existing capacity at call centers
  Service US/UK markets staffed at night
  Empty during day time  cheap, excess capacity
  World class technology already existing
Necessary conditions: information on govt process
  Resistance, lack of interest, lack of vision
  Use interns  get each ministry to check.
Competitive procurement
  Rules vs. Rules
“But how can private sector people answer government questions”?
  Under the radar implementation
  ‘Surprise’ soft launch

## Slide 17: First success story in e-Gov (and only success, for many years)
Call volume increase each year

## Slide 18
More calls answered than abandoned

## Slide 19
Government organizations showing increasing trust

## Slide 20: Turn-around in eGov
Re-thinking how systems are designed
  Modular (break down into parts)
  Open source
  In-house vs. outside development
Change in skill set of e-Gov team
  Serious ‘techies’ hired
  Chief Technology Officer Appointed
Local industry ‘taught’ how to bid, manage contract risk

## Slide 21: Today….
UN eGov rankings
  Sri Lanka made biggest jump (41 places)
  115th in (2012)
  74th in 2014
Actual service delivery: Since Sep 2013
  Hundreds of e-Services launched

## Slide 22: Did the structure make sense?
Notes: lady in the pink : Cho, IDI respondent from Mandalay. designs longyis. SEC E, no phone

## Slide 23: High salaries + uncontrolled publicity + high expectations  Recipe for failure?
You acquire detractors:
  People who applied for jobs, didn’t get hired
  People who didn’t like staff getting high salaries
  People who applied for pilot project grants, but didn’t get
  (Opposing) political parties
  …..
And when people over-promise/over-publicize
  Create unmet expectations
  Gives voice to detractors

## Slide 24: Could things have been done differently?
Could high salaries have been avoided?
  Important to attract Sri Lankans living overseas
  Important to attract private sector experts
Could the CEO have been more empowered within government
  Was not at Secretary level: practical difficulties due to protocol
Could ICTA have been more media savvy?
  Yes; today social media but then…
What other variables were available to play with?

## Slide 25: Implementers need policy direction during implementation, not just at the beginning
Population register
  A funder’s objections to religion/race being recorded
  Existing law/practices requires these (e.g. in inheritance)
  Changing this not a decision for the ICTA
  But technology workarounds possible
Free & open source
  Should they be given preference in procurement

## Slide 26: The Re-engineering Government Steering Committee that never was implemented
Senior civil servants
  Secretaries (~Deputy Ministers) of important departments [e.g. Ministry of Finance, Ministry of Public Administration, etc.
  Other senior actors
Taking policy level decisions
  With input from ICTA, industry
  Meeting regulatory, not annually
A vacuum when ICTA faced challenges
  Politicians stepping into that vacuum
ICTA: “the apex ICT policy making body for Sri Lanka and the implementer of the e-Sri Lanka vision”

## Slide 27: Why influence of ‘political power’ can be good
Politicians: voice of the people
  They SHOULD prioritize policies
To speak up for the implementing agency
  When it comes under attack
In theory, it opens doors
  Powerful people at the top
  Needed for cross sectoral agency
  Move from Ministry of Science and Technology  Prime Minister’s Office  President’s Office

## Slide 28: Why close ties to ‘political power’ can be bad
Politicians need
  ‘wins’ during their tenure
  Need to take care of their constituents  jobs
  Leading to local optimums, but not system-wide optimal solutions
  May not take technocratic input into consideration when making decisions
Results:
  Requests/orders to implement projects not in priority list
  Changes in ongoing project design (telecenters)
  ‘Appointment’ letters for people